## Sheet1
Level 1 | Level 2 | Level 3 | Level 4
1 Husky Air Project | 1.1 Project Management Process | 1.1.1 Prepare Project Charter | 1.1.1.1 Analyse Risks, Constraints, Assumptions
1.1.1.2 Assign Roles
|  | 1.1.2 Prepare Business Case | 1.1.2.1 Invlove stakeholders and get the reasoning for the project
|  | 1.1.3 Prepare Schedule | 1.1.3.1 Gather Individual Schedules of the Team
1.1.3.2 Optimize resource utilization and prepare a schedule
|  | 1.1.4 Assign Roles | 1.1.4.1 Assign the roles such that it fixes the accountability.
| 1.2 Data Collection | 1.2.1 Collect Data from pilots, passengers and make a table. | 1.2.1.1 Get the details of pilots.
1.2.1.2 Get the details of Passengers
|  | 1.2.2 Collect Volunteer Information | 1.2.2.1 Make a table with vounteer Information
|  | 1.2.3 Get the information of Clients and Aircrafts | 1.2.3.1 Make a table with Client Information
1.2.3.2 Get the information of Aircrafts and make a table.
| 1.3 Data Integration | 1.3.1 Identify the primary keys of the tables. | 1.3.1.1 Gather all the tables and identify unique columns.
|  | 1.3.2 Perform Normalization | 1.3.2.1 Identify Strong and weak entities.
1.3.2.2 Make a ER Diagram
1.3.2.3 Reduce Data Redundancy and improve Data Consistency.
|  | 1.3.3 Join the Tables. | 1.3.3.1 Join the tables based on common columns
| 1.4 User Interface Design | 1.4.1 User Interface Design Plan | 1.4.1.1 Prepare a Interface Design
1.4.1.2 Make it easy to navigate.
|  | 1.4.2 User Interface Design Execution | 1.4.2.1 Get web development resources.
1.4.2.2 Complete the design as per the plan.
| 1.5 Testing | 1.5.1 Implement Test Cases | 1.5.1.1 Prepare test Plan
1.5.1.2 Report back the bugs to the developers.
1.5.1.3 Test untill all bugs are fixed.
|  | 1.5.2 Performace Testing | 1.5.2.1 Let the system undergo stress testing
1.5.2.2 Identify the performce limits.
|  | 1.5.3 User Inteface Testing | 1.5.3.1 Check if the interface is consistent.
| 1.6 Support | 1.6.1 Netork Support
1.6.2 Operating Systems and Application support.
| 1.7 Closure | 1.7.1 System Acceptance | 1.7.1.1 Demonstrate system performace and get acceptance of Husky Air
|  | 1.7.2 Documentation | 1.7.2.1 Prepare necessary documentation that can make easy adoption of the system.